ASSIGNMENT 2: CONSTRUCTION ACTIVITIES AND PROCESS

BUILDING CONSTRUCTION 1 (ARC 1523)

NAME: MOHD SHAHRUL IZZAT BIN ABDULLAH

STUDENT ID: 0317185

LECTURER: MR. BRUCE LEE XIA SHENG

WEEK 1

CONSTRUCTION ACTIVITY:  Site Clearing and Earthwork

DURATION: 6 Days

EQUIPMENTS:

Machineries such as bulldozer, excavator, backhoe, roller truck.

Fencing material or boards according to size of site for site boundary, company placard, safety precautions signs, and tools.

SKILLED WORKER:

Civil Engineer, Ground engineer, Architect, site clearing supervisor, skilled machineries driver, experienced labors in site clearing process.

TECHNICAL INFORMATION:

- Provide the construction and completion of site clearance and earthwork around the site boundary comprising clearance of trees, shrubs, rubbish etc.

- Leveling cutting and filling to required platform level as Engineer’s requirement.

- Temporary works and other preparatory groundwork to achieve platform level and everything necessary and to move anything unnecessary materials debris etc.

- Meets the Architect’s satisfaction from the drawing and described in the specification.

WEEK 2

CONSTRUCTION ACTIVITY: Site Works, Installation of Temporary Facilities

DURATION: 3 Days

EQUIPMENTS: Tools, cabins, furniture.

SKILLED WORKER: Contractor, Labours, Site supervisor.

TECHNICAL INFORMATION:

- Provide hoarding or signboard

- Site office for consultant, contractor, meeting room, washroom

- Storage for materials such as cement, steel, sand, aggregate

- Provide access for loading and unloading

- Provide water supply

- Provide electricity

CONSTRUCTION ACTIVITY: Setting Out and Excavation

DURATION: 3 Days

EQUIPMENTS: Shovels, machineries such as excavator, backhoes, bulldozer

SKILLED WORKER: Experienced and skilled machineries drivers, site supervisor.

TECHNICAL INFORMATION:

- Establish a base line from which the whole building can be set out

- The position line is clearly marked on-site

- Digging the holes to place pile caps for foundations of the building.

WEEK 3

CONSTRUCTION ACTIVITY: Piling 1

DURATION: 6 Days

MATERIALS: Reinforced concrete, timber formwork, pre-stressed tendon

EQUIPMENTS: Bar bending machine, table saw, pile driver

SKILLED WORKER:

General worker for bar bending process, labours, pile driving driver, carpenter for formwork process, site supervisor

TECHNICAL INFORMATION:

Reinforced concrete piles are driven into the ground using a pile driver. While doing this process, the carpenter will prepare the formwork and insert reinforcement bar with concrete grade 30 for pile caps. Piling is also important to ensure the quality of the work and to prevent crack when the formwork is left there for two weeks.

WEEK 4

CONSTRUCTION ACTIVITY: Piling 2

DURATION: 6 Days

MATERIALS: Reinforced concrete, timber formwork, pre-stressed tendon

EQUIPMENTS: Bar bending machine, table saw, pile driver, tools

SKILLED WORKER:

General worker for bar bending process, labours, pile driving driver, carpenter for formwork process, site supervisor

TECHNICAL INFORMATION:

Reinforced concrete piles are driven into the ground using a pile driver. While doing this process, the carpenter will prepare the formwork and insert reinforcement bar with concrete grade 30 for pile caps. Piling is also important to ensure the quality of the work and to prevent crack when the formwork is left there for two weeks.

WEEK 5

CONSTRUCTION ACTIVITY: Pile Capping 1

DURATION: 6 Days

MATERIALS: Reinforced concrete, timber formwork

EQUIPMENTS: Bar bending machine, tools, table saw

SKILLED WORKER: General workers, labours, site supervisor

TECHNICAL INFORMATION:

- The reinforcement bar with concrete grade 30 for pile caps is put on the site

WEEK 6

CONSTRUCTION ACTIVITY: Pile Capping 2

DURATION: 6 Days

MATERIALS: Reinforced concrete, timber formwork

EQUIPMENTS: Bar bending machine, tools, table saw

SKILLED WORKER: General workers, labours, site supervisor

TECHNICAL INFORMATION:

- The reinforcement bar with concrete grade 30 for pile caps is put on the site

WEEK 7

CONSTRUCTION ACTIVITY: Stump from pile caps

DURATION: 6 Days

MATERIALS: Concrete grade 30, reinforcement bar, timber formwork

EQUIPMENTS: Bar bending machine, concrete vibrator, wood, tools.

SKILLED WORKER: Carpenters, general workers, labours

TECHNICAL INFORMATION:

- Stump is built to provide clearance for services such as plumbing and wiring. Stump is built on the slab.

WEEK 8

CONSTRUCTION ACTIVITY: Ground Beam 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement bar.

EQUIPMENTS: bar bending machine, concrete vibrator, tools

SKILLED WORKER: Carpenters, general workers, labours

TECHNICAL INFORMATION:

- The stumps on the slabs are connected to the ground beam for further support of foundation

WEEK 9

CONSTRUCTION ACTIVITY: Ground Beam 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement bar.

EQUIPMENTS: bar bending machine, concrete vibrator, tools

SKILLED WORKER: Carpenters, general workers, labours

TECHNICAL INFORMATION:

- The stump is connected to the ground beam for further support of foundation

WEEK 10

CONSTRUCTION ACTIVITY: Ground Floor Columns 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement bar.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools

SKILLED WORKER: Carpenters, general workers, labours

TECHNICAL INFORMATION:

- Column is built from the stump concrete of the foundation.

- Column is built as the structural framing of the house.

WEEK 11

CONSTRUCTION ACTIVITY: Ground Floor Columns 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement bar.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools

SKILLED WORKER: Carpenters, general workers, labours

TECHNICAL INFORMATION:

- Column is built from the stump concrete of the foundation.

- Column is built as the structural framing of the house.

WEEK 12

CONSTRUCTION ACTIVITY: Ground Floor Slab 1

DURATION: 6 days

MATERIALS: Concrete grade 30 (generic 150mm), timber formwork, reinforcement bar.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools.

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- Concrete is poured into the ground beams frame to create the ground floor.

WEEK 13

CONSTRUCTION ACTIVITY: Ground Floor Slab 2

DURATION: 6 days

MATERIALS: Concrete grade 30 (generic 150mm), timber formwork, reinforcement bar.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools.

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- Concrete is poured into the ground beams frame to create the ground floor.

WEEK 14

CONSTRUCTION ACTIVITY: First Floor Beam 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The construction of beams for the first floor is continued by connecting the columns to increase stabilization.

WEEK 15

CONSTRUCTION ACTIVITY: First Floor Beam 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The construction of beams for the first floor is continued by connecting the columns to increase stabilization.

WEEK 16

CONSTRUCTION ACTIVITY: First Floor Slab 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

- Concrete is poured into the frame work made around the first floor beams frame to create the first floor.

WEEK 17

CONSTRUCTION ACTIVITY: First Floor Slab 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

•	Concrete is poured into the frame work made around the first floor beams frame to create the first floor.

WEEK 18

CONSTRUCTION ACTIVITY:  First Floor Columns 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

- Column is built from the column built at the ground floor.

- Column is built as the structural framing of the house for the first floor.

WEEK 19

CONSTRUCTION ACTIVITY:  First Floor Columns 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

- Column is built from the column built at the ground floor.

- Column is built as the structural framing of the house for the first floor.

WEEK 20

CONSTRUCTION ACTIVITY:  Stairs to the First Floor

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The staircase is built to connect the ground floor to the first floor.

WEEK 21

CONSTRUCTION ACTIVITY: Second Floor Beam 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The beam construction is continued to the second floor by connecting the structural column of the first floor.

WEEK 22

CONSTRUCTION ACTIVITY: Second Floor Beam 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The beam construction is continued to the second floor by connecting the structural column of the first floor.

WEEK 23

CONSTRUCTION ACTIVITY: Second Floor Slab 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

•	Concrete is poured into the frame work made around the second floor beams frame to create the second floor.

WEEK 24

CONSTRUCTION ACTIVITY: Second Floor Slab 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

•	Concrete is poured into the frame work made around the second floor beams frame to create the second floor.

WEEK 25

CONSTRUCTION ACTIVITY:  Second Floor Columns 1

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

- Column is built from the column built at the first floor.

- Column is built as the structural framing of the house for the second floor.

WEEK 26

CONSTRUCTION ACTIVITY:  Second Floor Columns 2

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours.

TECHNICAL INFORMATION:

- Column is built from the column built at the first floor.

- Column is built as the structural framing of the house for the second floor.

WEEK 27

CONSTRUCTION ACTIVITY:  Stairs to the Second Floor

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The staircase is built to connect the ground floor to the second floor.

WEEK 28

CONSTRUCTION ACTIVITY: Roof Beam

DURATION: 6 Days

MATERIALS: Concrete grade 30, timber formwork, reinforcement.

EQUIPMENTS: Bar bending machine, concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: Carpenters, General workers, Labours

TECHNICAL INFORMATION:

- The beam construction is continued to the roof by connecting the structural column of the second floor.

- This beam acts as frame for the roof.

WEEK 29

CONSTRUCTION ACTIVITY: Ground Floor Bricks Walls 1

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, Steel trowel, Tools

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 30

CONSTRUCTION ACTIVITY: Ground Floor Bricks Walls 2

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, Steel trowel, Tools

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 31

CONSTRUCTION ACTIVITY: Ground Floor Bricks Walls 3

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, Steel trowel, Tools

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 32

CONSTRUCTION ACTIVITY:  Construction of the Overhanging Roof

DURATION: 6 Days

MATERIALS: Concrete, Timber formwork

EQUIPMENTS: Bucket, Concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours, Carpenter

TECHNICAL INFORMATION:

- Connected with the exterior walls of the ground floor to provide enough shades on the particular area.

WEEK 33

CONSTRUCTION ACTIVITY: First Floor Bricks Walls 1

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 34

CONSTRUCTION ACTIVITY: First Floor Bricks Walls 2

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 35

CONSTRUCTION ACTIVITY:  Construction of the Overhanging Roof

DURATION: 6 Days

MATERIALS: Concrete, Timber formwork

EQUIPMENTS: Bucket, Concrete vibrator, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours, Carpenter

TECHNICAL INFORMATION:

- Connected with the exterior walls of the first floor to provide enough shades on the particular area.

WEEK 36

CONSTRUCTION ACTIVITY: Second Floor Bricks Walls 1

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 37

CONSTRUCTION ACTIVITY: Second Floor Bricks Walls 2

DURATION: 6 Days

MATERIALS: Clay bricks, mortar

EQUIPMENTS: Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The exterior brick wall is created using the bricks to give the form of the house.

WEEK 38

CONSTRUCTION ACTIVITY: Roof Installation

DURATION: 6 Days

MATERIALS: Clay tiles, Structural steel frame

EQUIPMENTS: Tools, Scaffolding

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- Clay tiles roof installation

WEEK 39

CONSTRUCTION ACTIVITY: Door and Windows Frame Installation

DURATION: 6 Days

MATERIALS: timber and aluminium framing

EQUIPMENTS: Hammers, nails, L-rulers, tools

SKILLED WORKER: General workers, Labours, Carpenter

TECHNICAL INFORMATION:

- The frames for windows and doors is installed and acted as protection for the windows and doors.

WEEK 40

CONSTRUCTION ACTIVITY: Doors and Windows Installation

DURATION: 6 Days

MATERIALS: Chosen Windows and Doors

EQUIPMENTS: Hammer, Nails, Screwdriver, Screws, Tools

SKILLED WORKER: General workers, Labours, Carpenter

TECHNICAL INFORMATION:

- Windows and doors is installed after the frames are done.

WEEK 41

CONSTRUCTION ACTIVITY: Plumbing and Electrical Installation 1

DURATION: 6 Days

MATERIALS: Pipes and wires. (Suitable for house plumbing and electrical wiring-standards)

EQUIPMENTS: saw, pliers, cutters, sealers, tools

SKILLED WORKER: Plumber, Electrical Engineer, General Workers, Carpenter, Labours

TECHNICAL INFORMATION:

- Power sources and water supply is installed to the house according to the plan provided.

WEEK 42

CONSTRUCTION ACTIVITY: Plumbing and Electrical Installation 2

DURATION: 6 Days

MATERIALS: Pipes and wires. (Suitable for house plumbing and electrical wiring-standards)

EQUIPMENTS: saw, pliers, cutters, sealers, tools

SKILLED WORKER: Plumber, Electrical Engineer, General Workers, Carpenter, Labours

TECHNICAL INFORMATION:

- Power sources and water supply is installed to the house according to the plan provided.

WEEK 43

CONSTRUCTION ACTIVITY:  Wall and Ceiling Plastering 1

DURATION: 6 Days

MATERIALS: 15mm wall plaster, fiber glass gypsum for ceiling

EQUIPMENTS: Step ladders, Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The wall and ceiling is finished to provide the clean and beautiful view of the house.

WEEK 44

CONSTRUCTION ACTIVITY:  Wall and Ceiling Plastering 2

DURATION: 6 Days

MATERIALS: 15mm wall plaster, fiber glass gypsum for ceiling

EQUIPMENTS: Step ladders, Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The wall and ceiling is finished to provide the clean and beautiful view of the house.

WEEK 45

CONSTRUCTION ACTIVITY:  Wall and Ceiling Plastering 3

DURATION: 6 Days

MATERIALS: 15mm wall plaster, fiber glass gypsum for ceiling

EQUIPMENTS: Step ladders, Bucket, tools, scaffolding, steel trowel

SKILLED WORKER: General workers, Labours

TECHNICAL INFORMATION:

- The wall and ceiling is finished to provide the clean and beautiful view of the house.

WEEK 46 – WEEK 47

CONSTRUCTION ACTIVITY: Tiles Installation for Interior and Exterior

DURATION: 12 Days

MATERIALS: Marble tiles for living room and kitchen, solid timber flooring for bedroom, porcelain for wet kitchen, homogenous tiles for yard and terrace on ground floor and roof terrace, pebble wash for car porch and balcony, and mortar.

EQUIPMENTS: Tiles cutter, steel trowel, hammers and nails, tools

SKILLED WORKER: General Workers, Labours

TECHNICAL INFORMATION:

- Another finishing steps for the house, which is tiles installation. Various type of flooring is used to create a great look of the house inside.

WEEK 48 – WEEK 49

CONSTRUCTION ACTIVITY: Painting and Finishing exterior and interior

DURATION: 12 Days

MATERIALS: Primer, interior and exterior coloured paint, wire mesh.

EQUIPMENTS: brush rollers, step ladders and extension ladders, bristle brush, wire brush, paint scrapers, masking tape.

SKILLED WORKER: General Workers, Painters, Labours

TECHNICAL INFORMATION:

- Another finishing steps for the house, which is painiting. Various type of colours were used to create a great look of the house inside and outside.

WEEK 50 – WEEK 51

CONSTRUCTION ACTIVITY: Fixed furniture such lights, tables, drawers, cabinets, cupboards installation

DURATION: 12 Days

MATERIALS: Medium and soft wood, strong glue, varnish, paint, water heater, light bulbs, fixed electrical appliances

EQUIPMENTS: Hammers and nails, Table saw, utility cutters, tools

SKILLED WORKER: Electrical appliances expert, interior designer, general worker.

TECHNICAL INFORMATION:

- The process to beautify the house by installing the fixed furniture, cabinets, cupboards, tables etc. The right furniture will create the beautiful house interior. Normally, the interior designer is in charge to make sure the house is beautifully decorated.

WEEK 52

CONSTRUCTION ACTIVITY: Final Inspection

DURATION: 6 Days

MATERIALS: -

EQUIPMENTS: -

SKILLED WORKER: Contractors, Engineers, Developers.

TECHNICAL INFORMATION:

- After the house is completely finished, it is time for the contractors, engineers or developers to give it a look whether it meets the requirement or not. In this phase, the house must be well inspected to make sure it is safe to live.

WEEK 53

CONSTRUCTION ACTIVITY: Cleaning Site

DURATION: 6 Days

EQUIPMENTS: cloths, water cleaning agent, mop, broom, vacuum

SKILLED WORKER: General Workers

TECHNICAL INFORMATION:

- The house is cleaned up to get ready to be released to the customer.